## Schedule
Week | DayOfWeek | Date | PCB Hardware Tasks | GPU Tasks | Data Processing Tasks | CCU Tasks | Packaging Tasks | Senior Design Course Calendar | Cornell Cup Calendar
Phase 1
7 | Friday | 2013-10-04 | [5 empty] | Prelim PCB Layout Due |  | Notes: There are 8 weeks left, 7 of which are available for development. If it is assumed that each person spends 12hrs/wk on the project, then that means 84hrs total per person for the entire project. This is the total estimated time left for each team member.
7 | Saturday | 2013-10-05 |  |  |  |  | Find tinting for plexi glass
7 | Sunday | 2013-10-06 |  |  |  |  | Put existing materials together to make something that looks decent
8 | Monday | 2013-10-07 | [5 empty] | October Break
8 | Tuesday | 2013-10-08 | One to One placement of Parts on Board |  |  |  |  | October Break
8 | Wednesday | 2013-10-09 |  |  |  |  | Fix design so that it matches the expected design | Progress Briefing
8 | Thursday | 2013-10-10
8 | Friday | 2013-10-11 | [5 empty] | Formal Design Reviews
8 | Saturday | 2013-10-12 | Verify PCB against manufacturer requirements (Homework 7) and Submit PCB |  | Data Formats Calculated and Finalized
8 | Sunday | 2013-10-13
9 | Monday | 2013-10-14
9 | Tuesday | 2013-10-15
9 | Wednesday | 2013-10-16 | [5 empty] | Progress Briefing
9 | Thursday | 2013-10-17 | [6 empty] | Application Due
9 | Friday | 2013-10-18 | [5 empty] | Proof of Parts and PCB Submission
9 | Saturday | 2013-10-19 | Begin Parts Testing | Program that moves pacman on a fixed path | Sensor Processing Software Complete | Software that allows a game to be selected and load a game dynamically | Evaluate effect of focusing on user experience
9 | Sunday | 2013-10-20 |  |  | Software Interrupt that converts IMU and GPS data to units used by CCU and GPU
10 | Monday | 2013-10-21
10 | Tuesday | 2013-10-22
10 | Wednesday | 2013-10-23
10 | Thursday | 2013-10-24
10 | Friday | 2013-10-25 | [5 empty] | Software Design Narrative
10 | Saturday | 2013-10-26 | Test PCB Power Supply | Program that takes IMU data and uses that data to render pacman. | Create diagrams of expected network traffic flow for different packets.
10 | Sunday | 2013-10-27 | Solder Parts To Board
11 | Monday | 2013-10-28
11 | Tuesday | 2013-10-29
11 | Wednesday | 2013-10-30 | [6 empty] | Finalists Announced
11 | Thursday | 2013-10-31 | [6 empty] | Begin finalist info sessions
11 | Friday | 2013-11-01 | [5 empty] | Patent Liability Analysis
11 | Saturday | 2013-11-02 | Solder Parts To Board | Program that takes GPS data and uses that data to render pacman. |  | Create preliminary Library for PacMan game w/o networking
11 | Sunday | 2013-11-03 | Test PCB Microcontroller with LED Blinking Prog |  | Implement software that constantly listens for network traffic and responds.
12 | Monday | 2013-11-04 | [6 empty] | Team Commitment Date
12 | Tuesday | 2013-11-05 | [6 empty] | End finalist info sessions
12 | Wednesday | 2013-11-06
12 | Thursday | 2013-11-07
12 | Friday | 2013-11-08 | [5 empty] | Reliability and Safety Analysis
12 | Saturday | 2013-11-09 |  | Implement/Test data sending/receiving from GPU to f4.
12 | Sunday | 2013-11-10
13 | Monday | 2013-11-11
13 | Tuesday | 2013-11-12
13 | Wednesday | 2013-11-13
13 | Thursday | 2013-11-14 | [6 empty] | First Entry Online Chronicle due.
13 | Friday | 2013-11-15 | [5 empty] | Ethical and Enviro Impact
13 | Saturday | 2013-11-16 |  |  |  | Implement PacMan game based on virtual walls and virtual ghosts.
13 | Sunday | 2013-11-17 |  |  |  | Finish Library that uses networking to retrieve information about user position
14 | Monday | 2013-11-18
14 | Tuesday | 2013-11-19
14 | Wednesday | 2013-11-20
14 | Thursday | 2013-11-21
14 | Friday | 2013-11-22 | [5 empty] | User Manual Due
14 | Saturday | 2013-11-23
14 | Sunday | 2013-11-24
15 | Monday | 2013-11-25
15 | Tuesday | 2013-11-26
15 | Wednesday | 2013-11-27 | [5 empty] | Thanksgiving | Mid-review sign-ups open
15 | Thursday | 2013-11-28 | [5 empty] | Thanksgiving
15 | Friday | 2013-11-29 | [5 empty] | Thanksgiving
15 | Saturday | 2013-11-30
15 | Sunday | 2013-12-01
16 | Monday | 2013-12-02
16 | Tuesday | 2013-12-03
16 | Wednesday | 2013-12-04 | [5 empty] | PSSC Demos
16 | Thursday | 2013-12-05
16 | Friday | 2013-12-06 | [5 empty] | Project Showcase
16 | Saturday | 2013-12-07
16 | Sunday | 2013-12-08
17 | Monday | 2013-12-09 | [5 empty] | Finals Week Begins
17 | Tuesday | 2013-12-10 | [6 empty] | Mid-review sign-ups due
17 | Wednesday | 2013-12-11
17 | Thursday | 2013-12-12
17 | Friday | 2013-12-13 | [5 empty] | Semester Ends
17 | Saturday | 2013-12-14
17 | Sunday | 2013-12-15
Phase 2
|  |  | Hardware | Software | Packaging | Testing | Design Documentation
18 | Monday | 2013-12-16 | Update block diagram to reflect any changes to expected hardware begin | Assess software changes for Cornell Cup design begin | Re-approach head mounted packaging design begin | Intel Board Evaluation and Testing begin
| Tuesday | 2013-12-17 |  |  |  | Design/Choose system for gathering and maintaining status of user feedback begin
| Wednesday | 2013-12-18
| Thursday | 2013-12-19
| Friday | 2013-12-20
| Saturday | 2013-12-21
| Sunday | 2013-12-22
19 | Monday | 2013-12-23
| Tuesday | 2013-12-24
| Wednesday | 2013-12-25 | [5 empty] | Christmas
| Thursday | 2013-12-26
| Friday | 2013-12-27
| Saturday | 2013-12-28
| Sunday | 2013-12-29
20 | Monday | 2013-12-30
| Tuesday | 2013-12-31
| Wednesday | 2014-01-01
| Thursday | 2014-01-02
| Friday | 2014-01-03
| Saturday | 2014-01-04
| Sunday | 2014-01-05
21 | Monday | 2014-01-06
| Tuesday | 2014-01-07
| Wednesday | 2014-01-08
| Thursday | 2014-01-09
| Friday | 2014-01-10
| Saturday | 2014-01-11
| Sunday | 2014-01-12
22 | Monday | 2014-01-13 | [5 empty] | Classes Begin
| Tuesday | 2014-01-14
| Wednesday | 2014-01-15
| Thursday | 2014-01-16
| Friday | 2014-01-17
| Saturday | 2014-01-18
| Sunday | 2014-01-19
23 | Monday | 2014-01-20 | Lost Time (Death on Campus) | Lost Time (Death on Campus) | Lost Time (Death on Campus) | Lost Time (Death on Campus) | Lost Time (Death on Campus) | Martin Luther King
| Tuesday | 2014-01-21
| Wednesday | 2014-01-22
| Thursday | 2014-01-23 | [6 empty] | Start mid reviews
| Friday | 2014-01-24
| Saturday | 2014-01-25
| Sunday | 2014-01-26
24 | Monday | 2014-01-27
| Tuesday | 2014-01-28
| Wednesday | 2014-01-29
| Thursday | 2014-01-30
| Friday | 2014-01-31 | Lost Time (Death on Campus) | Lost Time (Death on Campus) | Lost Time (Death on Campus) | Lost Time (Death on Campus) | Lost Time (Death on Campus)
| Saturday | 2014-02-01
| Sunday | 2014-02-02 | Select Display, Select Battery, Select Fuel Guage, Select PSU design, Choose Wireless Technology begin | Re-design packet flows and software to allow any headset to be the ccu begin |  | Design/Choose system for gathering and maintaining status of user feedback end
24 | Monday | 2014-02-03 |  |  |  | Gather user feedback on current system
| Tuesday | 2014-02-04
| Wednesday | 2014-02-05
| Thursday | 2014-02-06
| Friday | 2014-02-07
| Saturday | 2014-02-08
| Sunday | 2014-02-09
25 | Monday | 2014-02-10 | [6 empty] | End mid reviews
| Tuesday | 2014-02-11
| Wednesday | 2014-02-12
| Thursday | 2014-02-13
| Friday | 2014-02-14
| Saturday | 2014-02-15 | Update block diagram to reflect any changes to expected hardware end |  |  | Intel Board Evaluation and Testing end | Update timeline to account for major design decisions
| Sunday | 2014-02-16 | Select Display, Select Battery, Select Fuel Guage, Select PSU design, Coose Wireless Technology end
26 | Monday | 2014-02-17 | Hardware and Software Design Review
| Tuesday | 2014-02-18
| Wednesday | 2014-02-19
| Thursday | 2014-02-20
| Friday | 2014-02-21
| Saturday | 2014-02-22 |  | Re-design packet flows and software to allow any headset to be the ccu end |  | Sensor data collection tests
| Sunday | 2014-02-23
27 | Monday | 2014-02-24 | Order Sensor PCB
| Tuesday | 2014-02-25 |  |  |  | Compare design with Google Glass and Oculus Rift
| Wednesday | 2014-02-26
| Thursday | 2014-02-27
| Friday | 2014-02-28
| Saturday | 2014-03-01 | Finalize Electrical Design | Port GPU software to Intel board
| Sunday | 2014-03-02
28 | Monday | 2014-03-03 | Order Power Supply PCB
| Tuesday | 2014-03-04
| Wednesday | 2014-03-05
| Thursday | 2014-03-06
| Friday | 2014-03-07 | [6 empty] | begin finalist info sessions
| Saturday | 2014-03-08 | Order Display, Battery, Fuel Gauage, PSU, other hardware
| Sunday | 2014-03-09
29 | Monday | 2014-03-10
| Tuesday | 2014-03-11
| Wednesday | 2014-03-12
| Thursday | 2014-03-13 | Sensor PCB Built and Tested
| Friday | 2014-03-14
| Saturday | 2014-03-15
| Sunday | 2014-03-16 |  | Assess software changes for Cornell Cup design end
30 | Monday | 2014-03-17 |  | Port software for collecting sensor data begin | Re-approach head mounted packaging design end Implemented new head mounted packaging |  |  | Spring Vacation
| Tuesday | 2014-03-18 |  | Port software for collecting sensor data end |  |  |  | Spring Vacation
| Wednesday | 2014-03-19 | [5 empty] | Spring Vacation
| Thursday | 2014-03-20 | [5 empty] | Spring Vacation
| Friday | 2014-03-21 | [5 empty] | Spring Vacation
| Saturday | 2014-03-22
| Sunday | 2014-03-23
31 | Monday | 2014-03-24
| Tuesday | 2014-03-25
| Wednesday | 2014-03-26
| Thursday | 2014-03-27
| Friday | 2014-03-28
| Saturday | 2014-03-29 |  | Port central control unit software to headset begin
| Sunday | 2014-03-30 |  | Port/update network traffic flow logic begin
32 | Monday | 2014-03-31 | Build power supply system (PCB and Battery).
| Tuesday | 2014-04-01
| Wednesday | 2014-04-02 |  |  |  | Power Supply Test
| Thursday | 2014-04-03
| Friday | 2014-04-04
| Saturday | 2014-04-05 |  | Port pacman simulation to Intel board
| Sunday | 2014-04-06 | Assemble all electrical hardware pieces
33 | Monday | 2014-04-07 | Combine packaging and electrical systems
| Tuesday | 2014-04-08 |  |  |  | Demonstrate Graphics and Head Tracking Functionality to Advisor
| Wednesday | 2014-04-09
| Thursday | 2014-04-10
| Friday | 2014-04-11
| Saturday | 2014-04-12
| Sunday | 2014-04-13
34 | Monday | 2014-04-14
| Tuesday | 2014-04-15 | [6 empty] | Wild card submission date
| Wednesday | 2014-04-16
| Thursday | 2014-04-17
| Friday | 2014-04-18 |  | Port central control unit software to headset end
| Saturday | 2014-04-19 |  | Port/update network traffic flow logic end
| Sunday | 2014-04-20 |  |  |  | Wireless packet flow testing (multiple headsets)
35 | Monday | 2014-04-21 |  |  |  | Multiple Headset simulation test |  |  | Final reports due
| Tuesday | 2014-04-22
| Wednesday | 2014-04-23 |  |  |  | Gather user feedback on current system
| Thursday | 2014-04-24
| Friday | 2014-04-25 | [6 empty] | end finalist info sessions
| Saturday | 2014-04-26
| Sunday | 2014-04-27
36 | Monday | 2014-04-28 | [5 empty] | Dead Week
| Tuesday | 2014-04-29 | [5 empty] | Dead Week
| Wednesday | 2014-04-30 | [5 empty] | Dead Week
| Thursday | 2014-05-01 | [5 empty] | Dead Week
| Friday | 2014-05-02 | [5 empty] | Dead Week | Final Competition in Florida

## Tasks
Task ID | Task to be completed | Deliverables | Dependent Taks IDs | Time to Complete | Actual Time
Beginning Expectation: Note that each person is expected to work 12hrs/week. This is because other commitments are expected. Thus, 12hr work assignment means the person will work all week on it. It is expected that productivity will diminish significantly in the transition between semesters. Tasks are referenced by task ID for dependencies. Phase 1 is mainly driven by a course schedule. Tasks in phase 1 may not explicitly have a deliverable, but it is implied by the task description
Final Expectation: In phase 2, each person was not able to work the expected number of hours per week initially because of a death on campus and later because of other commitments such as school and involvment with organizations. The number of hours per week was probably closer to 8hrs.
Legend
blue: subtask item has been added to schedule.
gold: Major Milestone
1 | Senior Design Tasks (Phase 1)
2
3
4
5
6 | PCB Hardware:
7
8 | One to One placement of Parts on Board |  |  | 3hr | 3hr
9 | Verify PCB against manufacturer requirements (Homework 7) and Submit PCB |  |  | 1hr
10 | Solder Parts To Board |  |  | 2 Weeks (24hrs)
11 | Test PCB Components
12 | Test PCB Power Supply
13 | Test PCB Microcontroller with LED Blinking Prog
14
15 | Other Hardware:
16
17 | Finish Packaging Design and Construction | Headset Prototype
18 | Put existing materials together to make something that looks decent |  |  | 1 Week (12hrs)
19 | Fix design so that it matches the expected design |  |  | 1hr
20 | Evaluate effect of focusing on user experience |  |  | 1 Week (12hrs)
21 | Find tinting for plexi glass |  |  | 5hrs | 5hrs
22
23
24
25
26
27
28
29
30
31
32
33 | Software:
34 |  | OpenGL GPU Software
35 | Implement Graphics Processing Software |  |  | 4 Weeks (48 hrs)
36 | Program that moves pacman on a fixed path |  |  | 1 Week (12hrs)
37 | Program that takes IMU data and uses that data to render pacman. |  |  | 1 Week (12hrs)
38 | Program that takes GPS data and uses that data to render pacman. |  |  | 1 Week (12hrs)
39 | Modify software to collect information from f4 |  |  | 1 Week (12hrs)
40
41 | Implement Central Control | End User Interface/Application
42 | Software that allows a game to be selected and load a game dynamically |  |  | 1 Week (12hrs)
43 | Create preliminary Library for PacMan game w/o networking |  |  | 1 Week (12hrs)
44 | Implement PacMan game based on virtual walls and virtual ghosts. |  |  | 1 Week (12hrs)
45 | Finish Library that uses networking to retrieve information about user position |  |  | 1 Week (12hrs)
46
47 | Implement f4 Sensor Processing Software | Documentation of data sizes and software.
48 | Software Interrupt that poll for IMU data |  |  | 1 Week (12hrs)
49 | Software Interrupt that polls for GPS data |  |  | 1 Week (12hrs)
50 | Software Interrupt that converts IMU data to units used by CCU and GPU |  |  | 1 Week (12hrs)
51 | Software Interrupt that converts GPS data to units used by CCU and GPU |  |  | 1 Week (12hrs)
52
53
54 | Write Protocol for f4 to GPU Communication | Data from sensors correctly used by GPU
55 | Decide in what format data will be pushed to GPU |  |  | 1 Week (12hrs)
56 | Implement/Test data sending/receiving. |  |  | 1 Week (12hrs)
57
58 | Write Protocol for f4 to CCU Communication | Correct packet flow betweeen devices.
59 | Finalize Packet Sizes and Data formats. |  |  | 1 Week (12hrs)
60 | Create diagrams of expected network traffic flow for different packets. |  |  | 1 Week (12hrs)
61 | Implement software that constantly listens for network traffic and responds. |  |  | 1 Week (12hrs)
62
63 | Cornell Cup Tasks (Phase 2) |  | 1
64 |  |  | 63
65 |  |  | 63
66 |  |  | 63
67 | Testing Work |  | 63
68 | Intel Board Evaluation and Testing | "Hello Wolrld" program for fpga and intel atom processor
69 | Power Supply Test | documented results | 63110
70 |  |  | 63
71 | Sensor data collection tests | Sample data and manual or scripted interpretation to validate. | 63, 141
72 |  |  | 63
73 |  |  | 63
74 | Wireless packet flow testing (multiple headsets) | Targeted test suite that excercises all flow paths. | 63, 146
75 | Test file transfer (image data) | Unit test that sends file and is verified for integrity at other end. | 63, 146
76 | Test starting/ending packets | Unit test | 63, 146
77 | Test headset losing/regaining wireless connection | Documented manual test results | 63, 146
78 | Test rendering of virtual objects with respect to geospatial location | Graphical documentation (video) | 63, 142
79 | Test rendering of virtual objects with respect to user head orientation | Graphical documentation (video) | 63, 142
80 |  |  | 63
81 | Multiple Headset simulation test | Graphical documentation (video) | 63, 147
82 | Gather user feedback on current system | entry in user feedback tracking system | 63, 112
83 | Design/Choose system for gathering and maintaining status of user feedback | system for tracking user feedback | 63
84 |  |  | 63
85 |  |  | 63
86 |  |  | 63
87 |  |  | 63
88 |  |  | 63
89 |  |  | 63
90 |  |  | 63
91 |  |  | 63
92 | Implementation Work |  | 63
93 |  |  | 63
94 |  |  | 63
95 | Hardware |  | 63
96 |  |  | 63
97 | Select Display | entry on hardware design wiki page | 63
98 | Select Battery | entry on hardware design wiki page | 63
99 | Select Fuel Gauge | entry on hardware design wiki page | 63
100 | Select PSU design | entry on hardware design wiki page | 63
101 | Choose Wireless Technology | entry on hardware design wiki page | 63
102 | Order Display, Battery, Fuel Gauage, PSU, other hardware | receipts | 63, 97, 98, 99, 100, 101
103 | Finalize Electrical Hardware Design | schematic and or diagram and or pcb | 63, 97, 98, 99, 100, 101
104 | Re-approach head mounted packaging design | cad drawing of chosen approach | 63
105 | Implement new head mounted packaging | physical headset and backpack. | 63, 103
106 |  |  | 63
107 |  |  | 63
108 | Hardware Design Review | Presentation and feedback | 103, 104
109 |  |  | 63
110 | Construct power supply system | power supply | 63, 108, 102
111 | Assemble all electrical hardware pieces | physical construction | 63, 108, 102, 110
112 | Combine packaging and electrical systems | physical construction of packaging and design | 63, 111, 105
113 |  |  | 63
114 | Update block diagram to reflect any changes to expected hardware | block diagram | 63
115 |  |  | 63
116 |  |  | 63
117 |  |  | 63
118 |  |  | 63
119 |  |  | 63
120 |  |  | 63
121 |  |  | 63
122 |  |  | 63
123 |  |  | 63
124 |  |  | 63
125 |  |  | 63
126 |  |  | 63
127 |  |  | 63
128 |  |  | 63
129 |  |  | 63
130 |  |  | 63
131 |  |  | 63
132 |  |  | 63
133 |  |  | 63
134 |  |  | 63
135 | Software |  | 63
136 |  |  | 63
137 | Assess software changes for Cornell Cup design. | Flow charts, pseudo code, diagrams | 63
138 | Re-design packet flows and software to allow any headset to be the ccu | flow charts, packet content specifications | 63
139 |  |  | 63
140 |  |  | 63
141 | Port software for collecting sensor data | code | 63, 103
142 | Port GPU software to Intel board | code | 63
143 |  |  | 63
144 | Update GPU software to account for new physical display. | code | 63, 103
145 | Port central control unit software to headset | code | 63, 103
146 | Port/update network traffic flow logic | code | 63, 145, 141
147 | Port pacman simulation to Intel board | code | 63, 146
148 | Software design review |  | 63
149 |  |  | 63
150 |  |  | 63
151 |  |  | 63
152 |  |  | 63
153 |  |  | 63
154 |  |  | 63
155 |  |  | 63
156 |  |  | 63
157 |  |  | 63
158 |  |  | 63
159 |  |  | 63
160 |  |  | 63
161 |  |  | 63
162 | Design Documentation |  | 63
163 | Update timeline to account for major design decisions | updated timeline | 63, 97, 98, 99, 100, 101, 137, 138
164 | Update block diagram to account for lessons learned (part of hardware design) | block diagram | 63
165 | Update software documentation from lessons learned (part of software design) | diagrams, flow charts | 63, 137, 138
166 | Create new cad of updated packaging design (part of packaging design) | cad drawing | 63
167 |  |  | 63
168