## Schedule
Week | DayOfWeek | Date | PCB Hardware Tasks | GPU Tasks | Data Processing Tasks | CCU Tasks | Packaging Tasks | Course Calendar
7 | Friday | 2013-10-04 | [5 empty] | Prelim PCB Layout Due | Notes: There are 8 weeks left, 7 of which are available for development. If it is assumed that each person spends 12hrs/wk on the project, then that means 84hrs total per person for the entire project. This is the total estimated time left for each team member.
7 | Saturday | 2013-10-05 |  |  |  |  | Find tinting for plexi glass
7 | Sunday | 2013-10-06 |  |  |  |  | Put existing materials together to make something that looks decent
8 | Monday | 2013-10-07 | [5 empty] | October Break
8 | Tuesday | 2013-10-08 | One to One placement of Parts on Board |  |  |  |  | October Break
8 | Wednesday | 2013-10-09 |  |  |  |  | Fix design so that it matches the expected design | Progress Briefing
8 | Thursday | 2013-10-10
8 | Friday | 2013-10-11 | [5 empty] | Formal Design Reviews
8 | Saturday | 2013-10-12 | Verify PCB against manufacturer requirements (Homework 7) and Submit PCB |  | Data Formats Calculated and Finalized
8 | Sunday | 2013-10-13
9 | Monday | 2013-10-14
9 | Tuesday | 2013-10-15
9 | Wednesday | 2013-10-16 | [5 empty] | Progress Briefing
9 | Thursday | 2013-10-17
9 | Friday | 2013-10-18 | [5 empty] | Proof of Parts and PCB Submission
9 | Saturday | 2013-10-19 | Begin Parts Testing | Program that moves pacman on a fixed path | Sensor Processing Software Complete | Software that allows a game to be selected and load a game dynamically | Evaluate effect of focusing on user experience
9 | Sunday | 2013-10-20 | Solder Parts To Board |  | Software Interrupt that converts IMU and GPS data to units used by CCU and GPU
10 | Monday | 2013-10-21
10 | Tuesday | 2013-10-22
10 | Wednesday | 2013-10-23
10 | Thursday | 2013-10-24
10 | Friday | 2013-10-25 | [5 empty] | Software Design Narrative
10 | Saturday | 2013-10-26 | Test PCB Power Supply | Program that takes IMU data and uses that data to render pacman. | Create diagrams of expected network traffic flow for different packets.
10 | Sunday | 2013-10-27 | Solder Parts To Board
11 | Monday | 2013-10-28
11 | Tuesday | 2013-10-29
11 | Wednesday | 2013-10-30
11 | Thursday | 2013-10-31
11 | Friday | 2013-11-01 | [5 empty] | Patent Liability Analysis
11 | Saturday | 2013-11-02 | Solder Parts To Board | Program that takes GPS data and uses that data to render pacman. |  | Create preliminary Library for PacMan game w/o networking
11 | Sunday | 2013-11-03 | Test PCB Microcontroller with LED Blinking Prog |  | Implement software that constantly listens for network traffic and responds.
12 | Monday | 2013-11-04
12 | Tuesday | 2013-11-05
12 | Wednesday | 2013-11-06
12 | Thursday | 2013-11-07
12 | Friday | 2013-11-08 | [5 empty] | Reliability and Safety Analysis
12 | Saturday | 2013-11-09 |  | Implement/Test data sending/receiving from GPU to f4.
12 | Sunday | 2013-11-10
13 | Monday | 2013-11-11
13 | Tuesday | 2013-11-12
13 | Wednesday | 2013-11-13
13 | Thursday | 2013-11-14
13 | Friday | 2013-11-15 | [5 empty] | Ethical and Enviro Impact
13 | Saturday | 2013-11-16 |  |  |  | Implement PacMan game based on virtual walls and virtual ghosts.
13 | Sunday | 2013-11-17 |  |  |  | Finish Library that uses networking to retrieve information about user position
14 | Monday | 2013-11-18
14 | Tuesday | 2013-11-19
14 | Wednesday | 2013-11-20
14 | Thursday | 2013-11-21
14 | Friday | 2013-11-22 | [5 empty] | User Manual Due
14 | Saturday | 2013-11-23
14 | Sunday | 2013-11-24
15 | Monday | 2013-11-25
15 | Tuesday | 2013-11-26
15 | Wednesday | 2013-11-27 | [5 empty] | Thanksgiving
15 | Thursday | 2013-11-28 | [5 empty] | Thanksgiving
15 | Friday | 2013-11-29 | [5 empty] | Thanksgiving
15 | Saturday | 2013-11-30
15 | Sunday | 2013-12-01
16 | Monday | 2013-12-02
16 | Tuesday | 2013-12-03
16 | Wednesday | 2013-12-04 | [5 empty] | PSSC Demos
16 | Thursday | 2013-12-05
16 | Friday | 2013-12-06 | [5 empty] | Project Showcase

## Tasks
Task to be completed | Time to Complete
PCB Hardware:
One to One placement of Parts on Board |  | X
Verify PCB against manufacturer requirements (Homework 7) and Submit PCB |  |  | X
Solder Parts To Board |  |  |  | X | X | X
Test PCB Components |  |  |  | X | X | X | X
Test PCB Power Supply |  |  |  | X | X
Test PCB Microcontroller with LED Blinking Prog | [6 empty] | X
Other Hardware:
Finish Packaging Design and Construction
Put existing materials together to make something that looks decent
Fix design so that it matches the expected design
Evaluate effect of focusing on user experience
Find tinting for plexi glass
Software:
Implement Graphics Processing Software | 4 Weeks (48 hrs) | X
Program that moves pacman on a fixed path | 1 Week (12hrs) | X | X
Program that takes IMU data and uses that data to render pacman. | 1 Week (12hrs)
Program that takes GPS data and uses that data to render pacman. | 1 Week (12hrs)
Modify software to collect information from f4 | 1 Week (12hrs)
Implement Central Control |  | X
Software that allows a game to be selected and load a game dynamically | 1 Week (12hrs)
Create preliminary Library for PacMan game w/o networking | 1 Week (12hrs)
Implement PacMan game based on virtual walls and virtual ghosts. | 1 Week (12hrs)
Finish Library that uses networking to retrieve information about user position | 1 Week (12hrs)
Implement f4 Sensor Processing Software |  | X
Software Interrupt that poll for IMU data | 1 Week (12hrs)
Software Interrupt that polls for GPS data | 1 Week (12hrs)
Software Interrupt that converts IMU data to units used by CCU and GPU | 1 Week (12hrs)
Software Interrupt that converts GPS data to units used by CCU and GPU | 1 Week (12hrs)
Write Protocol for f4 to GPU Communication |  | X
Decide in what format data will be pushed to GPU | 1 Week (12hrs)
Implement/Test data sending/receiving. | 1 Week (12hrs)
Write Protocol for f4 to CCU Communication |  | X
Finalize Packet Sizes and Data formats. | 1 Week (12hrs)
Create diagrams of expected network traffic flow for different packets. | 1 Week (12hrs)
Implement software that constantly listens for network traffic and responds. | 1 Week (12hrs)

## Gant Chart
Task | Week | 7 |  |  | 8 | [6 empty] | 9 | [6 empty] | 10 | [6 empty] | 11 | [6 empty] | 12 | [6 empty] | 13 | [6 empty] | 14 | [6 empty] | 15 | [6 empty] | 16
| DayOfWeek | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday
NOT COMPLETE | Date | time axis 2013-10-04 to 2013-12-06
Hardware:
One to One placement of Parts on Board | bar: 2013-10-08
Verify PCB against manufacturer requirements (Homework 7) and Submit PCB | bar: 2013-10-12
Solder Parts To Board
Test PCB Components
Test PCB Power Supply
Test PCB Microcontroller with LED Blinking Prog
Software:
Implement Graphics Processing Software
Program that moves pacman on a fixed path
Program that takes IMU data and uses that data to render pacman.
Program that takes GPS data and uses that data to render pacman.
Modify software to collect information from f4
Implement Central Control
Software that allows a game to be selected and load a game dynamically
Create preliminary Library for PacMan game w/o networking
Implement PacMan game based on virtual walls and virtual ghosts.
Finish Library that uses networking to retrieve information about user position
Implement f4 Sensor Processing Software
Software Interrupt that poll for IMU data
Software Interrupt that polls for GPS data
Software Interrupt that converts IMU data to units used by CCU and GPU
Software Interrupt that converts GPS data to units used by CCU and GPU
Write Protocol for f4 to GPU Communication
Decide in what format data will be pushed to GPU
Implement/Test data sending/receiving.
Write Protocol for f4 to CCU Communication
Finalize Packet Sizes and Data formats.
Create diagrams of expected network traffic flow for different packets.
Implement software that constantly listens for network traffic and responds.