## Slide 1: Augmented Reality Cornell Cup Mid Review Fall 2012
Stephen Carlson
Stephen Ellis
Thor Smith
Thor
Smith
Steven
Ellis
Stephen
Carlson

## Slide 2: Outline
Challenge Definition
Project Entry Solution
Accomplishments to Date
Technical Ingenuity
Project Execution Overview
Complications
Opportunities
Recommendations and Next Steps

## Slide 3: Challenge Definition
Wearable computing is emerging quickly
  Google Glass, Samsung Galaxy Gear, and Oculus Rift.
Combine virtual reality with reality to create augmented reality
  Provide information
  Promote Teamwork
  Decrease need for physical objects
The design will need to satisfy the following requirements:
  Portable and Comfortable
  Track user position and head orientation
  Wireless Communication
  Easy to set up and use
  Transparent display, easy to see

## Slide 4: USE cases
Artistic Performance
  Performers need to know where to be and when.
Train a New Employee
  Show a physical demonstration of equipment
  Employee may observe machinery in operation.
Children Playing Games
  Children Rely on “imaginary” objects placed in a select location.
Educational Demonstrations
  Replace resources with virtual resources placed in appropriate locations.

## Slide 5: Project entry solution
Will not focus on internet connectivity
Allow for multiple simulations.
Focus on Gaming
Headset:
  Provide the display
  Mounting point for sensors
Backpack:
  Wireless communication
  Graphics rendering
  Simulation Logic

## Slide 7: Accomplishments To Date
PHASE 1
PHASE 2

## Slide 8: Accomplishments To Date (PHA1)
Hardware
  Interfacing to Inertial Measurement Unit
  Interfacing to GPS
  Power management
    Battery charging
    Battery fuel gauge
    Voltage regulation

## Slide 9: Accomplishments To Date (PHA1)
Self-contained headset
  Hard hat with display and all
  electronics mounted to rails
Software
  OpenGL ES for 3D rendering
  Networking: XBees with CCU
  SPI communication between Pi and micro
  MacPan game

## Slide 10: Performance metrics
Metric | Initial Target | Phase 1 (Measured) | Phase 2 (Current Estimate)
Mass | Headset: 1 kg Backpack: 3 kg | Headset: 1.3kg Backpack: N/A | Headset: ~1kg Backpack: ~2.5kg
Power | 3 hours runtime | ~3 hours | ~4 hours
Location Accuracy | 2 meters | TODO | Same as Phase 1
Wireless Range | 80 m range, line of sight | TODO | TODO
Display Refresh Rate | 20 FPS | 30 FPS | 60 FPS
Network Refresh Rate | 20 FPS | N/A | 60 FPS
Usability | End user can start up and use device without a technician | Turnkey startup | Turnkey startup

## Slide 11: Accomplishments To Date (PHA2)
Power consumption testing
  Provided Terasic board uses 1.2 A typical (14.4 W)
  Acceptable battery life with 60 Whr capacity
Hardware design for Phase 2
  Power supply design
    Battery and regulator selection
  Headset interfacing board
    Re-use GPS, inertial measurement unit,
    microcontroller
Packaging
  Re-use optics
  Selected new display
  Selected helmet and backpack
[POWER CONSUMPTION]
[PCB]

## Slide 12: Technical Ingenuity
Display virtual environment overlay on real world
  Preserves real-world depth perception
  Large field of view
  Both worlds perceptible simultaneously
User head and position tracking
  Filtering algorithm for inertial measurement data
Portability and battery operation
Wireless communication to other headsets
  Multi-user augmented reality

## Slide 13: Execution overview – Timeline 1/3

## Slide 14: Execution overview – Timeline 2/3

## Slide 15: Execution Overview – Timeline 3/3

## Slide 16: Execution overview - BUDGET
Name | Item | Vendor | Unit Price | Shipping | Quantity | Price
Battery |  | BatterySpace | 66.95 |  | 2 | 133.9
Screen1 |  | AdaFruit | 139.95 |  | 1 | 139.95
Screen2 |  | AdaFruit | 64.95 |  | 1 | 64.95
IMU |  | Mouser | $28.75 |  | 1 | 28.75
GPS |  | SparkFun | 49.99 |  | 1 | 49.99
Passives |  | Various | 10 |  | 2 | 20
PCB |  | Oshpark | 40 |  | 2 | 80
Microcontroller |  | DigiKey | 11.45 |  | 2 | 22.9
Charger |  | BatterySpace | 39.95 |  | 2 | 79.9
Regulator |  | Mouser | 13.23 |  | 2 | 26.46
Fuel Guage |  | DigiKey | 6.43 |  | 2 | 12.86
3D printed Box |  | Purdue IEEE | 40 |  | 2 | 80
Backpack | Draw String Backpack | Supplied | 10 |  | 0 | 0
Total |  |  | 521.65 |  |  | 739.66

## Slide 17: COMPLICATIONS
Patent Liability
  Novelty of design avoids many AR patents
    Large fraction specifically mention cameras
  Licensing may be required
  Could file new patents and cross-license
User Safety
  LiFePO4 much safer than other Lithium battery chemistries
  Translucent display keeps user aware of environment
  Product unsuitable for use while driving, operating heavy machinery

## Slide 18: Opportunities
Selling software to users after purchase of device
  Need to set up distribution network
  Encourage third party development
  Anti-piracy solutions

## Slide 19: Recommendations and Next Steps
Continued software development
  Improve calculation of head orientation
  Improve filtering of GPS data
Migrate software to new motherboard
Finalize packaging modifications for larger display
Testing of new hardware
  Battery power and charging
  Interfacing of Terasic board with existing microcontroller
  Display

## Slide 20: Questions / Discussion

## Slide 21: PCB

## Slide 22: Schematic